## MonkeyBox
Department | Task List
Admin | Main Master Management Dashboards
App / Frontend | Referrals improve -Incentive discussion and Possible UI Changes
App + Web | Sign up flow and log in flow need to be seperated
Backend | Data Privacy Compliance
Backend | User Data Encryption
backend | Subscription overlapping
Backend | Automation of Holiday Calender
Backend | changing the auto order time to 11:45
Backend / Admin | Waiting List for Schools (for school not found) -- Move to prod from UAT
Backend / Admin | Omak Menu In admin
Backend / Admin | CityWise Admin and Super Admin Module
Backend / Server | Scheduled Backup and Scripts for Site Recovery
Backend / Server | Disaster Recovery Planning
Feature Requests | In-App Notifications
Feature Requests | Integration of ZILLSKILL features
Feature Requests | Gamification and Engagement
Feature Requests | Community of Monkey Parents
Feature Requests | Daily Challanges
Feature Requests | Daily News
Feature Requests | Quizzes
Feature Requests | Reward Store & Wallet
Feature Requests | Birthday Campaign
Feature Requests | Separate Admin Systems
Feature Requests | Netsuite integration
Feature Requests | Cross-Selling and Up-Selling
Feature Requests | Super App Concept Exploration
Feature Requests | Reporting Issues and Report KT
Feature Requests | MIS Reports for MonkeyBox
Feature Requests | Reporting and Analytics Expansion
Feature Requests | School Communication
Feature Requests | Additional Implementations: Main Reporting Website, Health Checkup Website, Alert System
Feature Requests | Github Integration and CI/CD pipeline
Improvement / Backend / Admin | Smooth Menu Upload Process for MonkeyBox - Menu Upload Optimization - Automation of Nutrition and Portioning
Improvements | Multiple days order in cart place with single transaction.
Improvements | When Buy plan Wallet balnce consider and remaining amout get from razorpay
Improvements | OTP not being delivered
Improvements / DevOps | Real-time Data Monitoring
Improvements / DevOps | More Control to User for Order and Account Management
Improvements / DevOps | Database Optimization
Improvements / DevOps | Scalability Enhancements
Improvements / DevOps | Load Balancing
Improvements / Tech Stack | SEO Website Enhancement
Product Analytics | Posthog Integration for analytics
Product Analytics | Webenage New model -Event Creation and update existing events -Funnel Creation and Dropping Rate -Better Analytics on Campaigns and Referrals -New user Journeys with subscription promotion -User Segmentation Webenage Notification issue
Product Management | Daily Dish highlights - Daily Promotional notificaton
Product management | Subscription promote banner on home and cart page.
Product management | Separate Pause/reorder and cancel plan
Web | MonkeyBox Website UI/UX Revamp
Web | MonkeyBox Blogs and Articles websites

## Combo Co
Combo@Co.
AWS - GCP Migration :- Combo@Co.
App Revamp | UI Enhancement
Order Placement Efficiency
Performace Measurements and Optimisation
Sign up flow and log in flow need to be seperated
SEO Enhancement
Features | Coupon Code with CashBack Option
Referrals improve
Feedback Mechanism
Increase User time | In-App Notifications
In-App Engagement
Daily Challanges
Daily News
Quizzes
Reward Store & Wallet
Admin | Smooth Menu Upload Process for Combo@co. - Menu Upload Optimization - Automation of Nutrition and Portioning
Data Analytics | Implementing Analytics
Funnel Creation and Dropping Rate
Better Analytics on Campaigns and Referrals
Data, database & Infrastructure | Scalability Enhancements
Load Balancing
Database Optimization
Data Privacy Compliance
Real-time Data Monitoring
User Data Encryption
POWER BI with Combo@co
Combo@Co App Deployment
Combo@Co Website and Admin Panel
Combo@Co Landing Page with Full Week Menus
Combo@Co Delivery App
Combo@Co Domain Setup
Combo@Co IOS and Google PlayStore Account App Updates
Automation of Holiday Calender
Birthday Campaign

## Reports and Analytics tasks
Report Name | Description
Correct Data | If I Download the report, will come some value and after some times will come other Value, for that we need to fix the data.
User Statistics | Total Users - (students, parents, and schools)
Active Users - Number of users actively using the app daily, weekly, and monthly.
User Growth - ( Trends and changes in user registration over time)
Breakdown
Order Statistics | Total Orders - (Total number of food orders placed)
Order Frequency: Average number of orders per user.
Popular Items: Most frequently ordered meals or food items.
Order Trends - (daily, weekly, monthly)
Delivery Performance | On-Time Delivery: Percentage of orders delivered on time.
Average Delivery Time: Time taken from order placement to delivery.
Delivery Issues: Number and type of delivery issues reported (late delivery, incorrect orders, etc.).
Marketing and Engagement | How many users getting the notification messages and view the applications
unreceived notification - to the customer
Visualizations | Dashboards: Interactive dashboards that allow team members to explore data in real-time.
Financial Reports | Date , School name, POD ID & Name, Meal Type, number of order , cost
Exrra box report , Without extra box report
Order summary report - with all the kitchens
Daily sales report over all
Menu | menu editing ( pirce, Des) with spl approval before the upload - grammar
if anything we do for the wrong( North and south menu ), it won't go to the next stap.
Best order report
Notification | sending bulk sms to the parents regarding missing lunch or breakfast orders if found missing at the breaktime to contact Particular point of contact person
Menu should be published completely what we are sending all the items should know to everyone which helps to orders flow
Add | add option ( feedback ) to parents so they can share their feedback & will be helpful to correction
add staff ( teacher) option to place them order
add birthday wishes to students in app - get approval with parents
sending whatsapp ,or mail to parents , regarding about students didn't return box back , will helpful to recover our box on that day .
The menu for the whole week (previous day and existing day) should be visible to end user throughout the week to understand the menu but should not be able to place order
Automated push message to parents registered number if the box is not returned
Delivery Time | Kitchen, School, No of box. timing
Xto10X Reports | users joined in june month
users joined in june and never order
users joined in june and order atleast once
users joined in june and 0 kids
last 2 and 3 months light-lapsers users data
month and school wise mealtype's revenue, order quantity and extrabox
parent and child data wi no of children, no child for placing order and no of child for whom not placing order
school wise number of kids, and number of active kids
last 3 years comparison of this report (month and school wise mealtype's revenue, order quantity and extrabox)
top selling items
Query to find users who have installed the app from January 2024 to the upcoming date
menu details after which menu user stopped placing order
active users by school wise and by month wise
different month wise or last 2,3 months users data. like who installed app, who placed orders atleast once, who never order.

## Task
Task | Status | Completed On
V3 Timeline | Done | May | Timeline Monkeybox V3
Tech Team June Task | Done |  | June Completed Tasks
App V4 Launch | Done | 15th sept
Web Revamp | Ongoing
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do
To do

## Overall Backlog (require update
Department | Epic | Task no. | Task List | Status | Timeline | Design Work | FrontEnd Work | Backend Work | App Work | Testing Work | KT Session and Hanover to OPS Team
MonkeyBox
| Revemp |  | MonkeyBox App UI/UX Revamp | J-Done | 8 week | 3 weeks | 5 week | 5 week | 5 week | 3 week | 1 week
|  |  | UI Enhancement | J-Done
|  |  | Order Placement Efficiency | Done in PRD
|  |  | Performace Measurements and Optimisation | Done in PRD | 2 week | 0 | 1 week
|  |  | SEO Enhancement | J-Done
| Features |  | Coupon Code with CashBack Option | J-Done | 1 week
|  |  | Referrals improve | J-Done | 1 week
| Data analytics |  | Funnel Creation and Dropping Rate -Better Analytics on Campaigns and Referrals | J-Done
|  |  | Implementing Analytics |  | 2 week
| Admin |  | Creating Waiting List for Schools (for school not found) | J-Done
|  |  | Smooth Menu Upload Process for MonkeyBox - Menu Upload Optimization - Automation of Nutrition and Portioning | J-Done | 6 week
|  |  | Omak Menu In admin | J-Done |  | 0 | 1 week | 2 week | 0 | 3 days | 2 days
| Increase user time in app |  | In-App Notifications | J-Done | 2 week
|  |  | In-App Engagement | no need | 2 week
|  |  | Integration of ZILLSKILL features | no need | 4 week | 2 weeks | 4 week | 4 week | 4 week | 2 week | 2 days
|  |  | Gamification and Engagement | no need
|  |  | Daily Challanges | J-Done | 1 week
|  |  | Daily News | J-Done | 1 week
|  |  | Quizzes | J-Done | 1 week
|  |  | Reward Store & Wallet | J-Done | 1 week
| Data, Database & Privacy |  | Real-time Data Monitoring | J-Done | 3 week
|  |  | POWER BI with MonkeyBox | J-Done | 1 week
|  |  | Database Optimization | J-Done
|  |  | Data Privacy Compliance | J-Done
|  |  | User Data Encryption | J-Done
|  |  | Scalability Enhancements | J-Done | 3 week
|  |  | Load Balancing | J-Done
| Customer Feedback & Support |  |  | J-Done
|  |  | Automation of Holiday Calender |  | 1 week
Birthday Campaign
MonkeyBox Website UI/UX Revamp
|  |  | AWS - GCP Migration :- Monkeybox |  | Almost done
|  |  | Sign up flow and log in flow need to be seperated |  | 2 week
|  |  | More Control to User for Order and Account Management |  | 8 week
Scheduled Backup and Scripts for Site Recovery
Disaster Recovery Planning
CityWise Admin and Super Admin Module
Separate Admin Systems
Main Master Management Dashboards
Netsuite integration
Cross-Selling and Up-Selling
Super App Concept Exploration
|  |  | changing the auto order time to 11:45 |  | 1 day
|  |  | Reporting Issues and Report KT |  | 1 week
|  |  | MIS Reports for MonkeyBox |  | 1 week
Reporting and Analytics Expansion
School Communication
|  |  | Additional Implementations: Main Reporting Website, Health Checkup Website, Alert System |  | 3 week
Combo@Co.
|  |  | AWS - GCP Migration :- Combo@Co. |  | Almost done
| App Revamp |  | UI Enhancement
Order Placement Efficiency
|  |  | Performace Measurements and Optimisation |  | 2 week | 0 | 1 week
|  |  | Sign up flow and log in flow need to be seperated |  | 2 week
SEO Enhancement
| Features |  | Coupon Code with CashBack Option |  | 1 week
|  |  | Referrals improve |  | 1 week
|  |  | Feedback Mechanism |  | 2 week
| Increase User time |  | In-App Notifications |  | 2 week
|  |  | In-App Engagement |  | 2 week
|  |  | Daily Challanges |  | 1 week
|  |  | Daily News |  | 1 week
|  |  | Quizzes |  | 1 week
|  |  | Reward Store & Wallet |  | 1 week
| Admin |  | Smooth Menu Upload Process for Combo@co. - Menu Upload Optimization - Automation of Nutrition and Portioning |  | 6 week
| Data Analytics |  | Implementing Analytics |  | 2 week
Funnel Creation and Dropping Rate
|  |  | Better Analytics on Campaigns and Referrals |  | 2 week
| Data, database & Infrastructure |  | Scalability Enhancements |  | 3 week
Load Balancing
Database Optimization
Data Privacy Compliance
|  |  | Real-time Data Monitoring |  | 3 week
User Data Encryption
|  |  | POWER BI with Combo@co |  | 1 week
|  |  | Combo@Co App Deployment |  | Done
|  |  | Combo@Co Website and Admin Panel |  | 3 week
|  |  | Combo@Co Landing Page with Full Week Menus |  | 1 week
|  |  | Combo@Co Delivery App |  | 2 week
Combo@Co Domain Setup
|  |  | Combo@Co IOS and Google PlayStore Account App Updates |  | Done
|  |  | Automation of Holiday Calender |  | 1 week
Birthday Campaign