## Roadmap
Tasks List | Oct'24 |  |  |  | Nov'24
Monkeybox Web revamp (New UI according to new app version) | Frontend Web Dev
Tester
Waiting List for Schools (for school not found) Move to prod from UAT | Frontend/Backend Web Dev
Menu - Admin Changes (-Smooth menu upload process (Move to Prod) & Omak Menu Process) |  | Frontend/Backend Web Dev
Handling No Menu (Freeze date scrolling for current week) |  | Frontend/Backend Web Dev
Webengage New Model or Alternetive (New event creation & journey and campaign creation) | PM
Flutter Development
Subscription and other Promotion (Banner for Subscription, Wallet Recharge and Ad-hoc orders) | PM
Code Reflactor (Performance improvements) | Flutter Development
Refer and Earn (Incentivization) |  |  | PM
Flutter Development
Reporting - Admin (Finance Reports UI Changes & School reports UI Changes) |  |  |  | PM
Frontend/Backend Web Dev
Subscription overlapping (Resolve subscription overlapping isuue) |  |  | PM
Frontend/Backend Web Dev
GitHub Integration and CI/CD pipeline (For better tracking of the development cycle) | [5 empty] | Dev team
Novo Labs Technologies Website (Implement a new website for Novo Labs technologies) |  |  |  |  | PM
UI/UX desinger
Frontend/Backend Web Dev
Tester
Automation of Holiday Calender |  |  |  |  | Backend Dev
New Analytics tool Integration (Find new tool and integrate with our system) | [5 empty] | PM
Flutter Development
Backend Dev
In-App Notifications (For Increased User app time) |  |  |  | PM
UI/UX desinger
Flutter Development
Backend Dev
Specific Subscription promotion on cart page (Encouraging user to upgrade plan) | [6 empty] | PM
Flutter Development
Backend Dev